## tasks
task_title | time_stamp | start_flag | end_flag | risk | difficulty | r_hardware | r_software | r_people | r_consumables | r_attire | r_tools
AAO- Stowage Planning | 5 | 1 | 0 | 0.4 | 0.7 |  |  | 0.3
AAO- Stowage Planning | 7 | 0 | 0 | 0.2 | 0.65 |  |  | 0.25
AAO- Stowage Planning | 9 | 0 | 0 | 0.3 | 0.5 |  |  | 0.22
AAO- Stowage Planning | 11 | 0 | 1 | 0.1 | 0.4 |  |  | 0.1
ABO - Vessel schedule | 3 | 1 | 0 | 0.7 | 0.9 |  | 0.1 | 0.6
ABO - Vessel schedule | 6 | 0 | 1 | 0.4 | 0.5 |  | 0.1 | 0.5
ACO - Safety/Security mangament | 1 | 1 | 0 | 0.1 | 0.2 |  |  | 0.2 |  | 0.2
ACO - Safety/Security mangament | 5 | 0 | 0 | 0.42 | 0.28 |  |  | 0.56 |  | 0.84
ACO - Safety/Security mangament | 10 | 0 | 0 | 0.5 | 0.3 |  |  | 0.3 |  | 1
ACO - Safety/Security mangament | 15 | 0 | 0 | 0.4 | 0.45 |  |  | 0.45 |  | 0.8
ACO - Safety/Security mangament | 21 | 0 | 0 | 0.3 | 0.44 |  |  | 0.44 |  | 0.6
ACO - Safety/Security mangament | 25 | 0 | 0 | 0.1 | 0.4 |  |  | 0.8 |  | 0.1
ACO - Safety/Security mangament | 31 | 0 | 1 | 0.08 | 0.12 |  |  | 0.12 |  | 0.16
BAO - Railcar unloading | 15 | 1 | 0 | 0.05 | 0.7 | 0.6 |  | 0.1 |  |  | 0.8
BAO - Railcar unloading | 17 | 0 | 1 | 0.02 | 0.7 | 0.2 |  | 0.1 |  |  | 0.8
BBO - Cargo staging | 15 | 1 | 0 | 0.12 | 0.5 |  | 0.1 | 0.4 | 0.2
BBO - Cargo staging | 17 | 0 | 1 | 0.1 | 0.45 |  | 0.12 | 0.3 | 0.2
BBA - Fueling | 18 | 1 | 0 | 0.05 | 0.1 | 0.3 |  |  | 0.8
BBA - Fueling | 19 | 0 | 1 | 0.02 | 0.05 | 0.35 |  |  | 0.9
BCO - Scanning / RFID | 15 | 1 | 0 | 0.6 | 0.7 | 0.05 | 0.05 |  |  |  | 0.28
BCO - Scanning / RFID | 16 | 0 | 0 | 0.4 | 0.6 | 0.2 | 0.29 |  |  |  | 0.27
BCO - Scanning / RFID | 17 | 0 | 1 | 0.4 | 0.45 | 0.21 | 0.05 |  |  |  | 0.16
CAO - Roll - on | 20 | 1 | 0 | 0.9 | 0.8 | 0.45 | 0.21 | 0.5 | 0.2 |  | 0.6
CAO - Roll - on | 22 | 0 | 1 | 0.1 | 0.5 | 0.38 | 0.14 | 0.5 | 0.21 |  | 0.52
CBO - Cargo stowage | 20 | 1 | 0 | 0.85 | 0.9 | 0.05 | 0.12 | 0.6 | 0.5 |  | 0.9
CBO - Cargo stowage | 21 | 0 | 0 | 0.72 | 0.8 | 0.05 | 0.21 | 0.3 | 0.4 |  | 0.5
CBO - Cargo stowage | 22 | 0 | 1 | 0.45 | 0.2 | 0.05 | 0.03 | 0.3 | 0.3 |  | 0.4
CBA - Strapping | 20 | 1 | 0 | 0.05 | 0.2 | 0.05 | 0.21 | 0.5 | 0.4 | 0.2 | 0.6
CBA - Strapping | 22 | 0 | 1 | 0.02 | 0.1 | 0.05 | 0.12 | 0.4 | 0.2 | 0.2 | 0.5
DAO - Ourturn Reporting | 23 | 1 | 0 | 0.45 | 0.3 |  |  | 0.3
DAO - Ourturn Reporting | 24 | 0 | 1 | 0.3 | 0.15 |  |  | 0.3